## How to use
SPL MANAGEMENT |  | Corrective Action Log
Corrective Action Log
Findings from inspections, walk-throughs, incidents, and audits, tracked until someone has checked the fix.
Intended for: managers and compliance leads tracking findings from inspections, walk-throughs, incidents, and audits. ¦ Version 2.0 · Content reviewed September 26, 2026
1 | Replace or delete the rows marked EXAMPLE. Add one row per finding, per location, on the day it is found.
2 | Log findings from every source, not only regulator visits. Pick the Source from the dropdown.
3 | Write the Finding as a plain fact. In Root cause, say why it happened, not only what happened.
4 | Give each corrective action one named owner and a due date. If a regulator set a response deadline, use it and keep proof of what you sent and when.
5 | For an immediate hazard, such as a blocked exit, contain it at once and log that as its own row, closed the same day. Then add a separate row for the step that prevents a repeat, with its own owner and date.
6 | When the owner finishes, set Status to Done: awaiting check and enter a Verify by date. Mark it Verified closed only after someone other than the owner checks that the fix works.
7 | In Evidence / record location, say exactly where the proof is kept, so authorized staff can retrieve it within any applicable response period and within your own internal retrieval target.
8 | Review the log at each monthly compliance review. Look for the same root cause at more than one location, and share each fix with the other sites.
Two kinds of overdue
Work overdue: the due date has passed and the work is not done. The row shows red. Verification overdue: the work is marked done, but the Verify by date has passed without a check. The row shows gold with bold red text. The Overdue flag column names which one applies, and a row stays open until it is Verified closed.
What the colors mean
Red: work overdue. Gold: done and awaiting check. Gold with bold red text: verification overdue. The summary above the log counts open items, work overdue, awaiting check, verification overdue, and verified closed this month. The colors are highlights in this workbook only; no email or other alerts are sent.
Suggested cadence
Suggested cadence only, not a requirement. Where a law, license condition, lease, or insurer sets a different frequency or deadline, follow that instead.
Before you rely on it
Requirements vary by jurisdiction and change often. Confirm response deadlines and record retention periods with your regulator or a qualified professional.
Prepared by SPL Management
Want a second set of eyes? spl-management.com/consultation
SPL Management · spl-management.com · Managed with Precision
General information only. Requirements vary by jurisdiction and change often; confirm current rules with your regulator or a qualified professional.

## Log
SPL MANAGEMENT | [13 empty] | Corrective Action Log
Rows marked EXAMPLE are samples: replace or delete them. Red = work overdue. Gold = done, awaiting check. Gold with bold red text = verification overdue.
Summary | Open | Work overdue | Awaiting check | Verification overdue | Verified closed this month | Open counts every row with a Finding that is not Verified closed. Work overdue: past the due date and not done. Verification overdue: done, but not checked by the Verify by date. Counts update on their own.
ID | Date found | Location | Source | Finding | Root cause | Corrective action | Owner (named person) | Due date | Status | Overdue flag | Verify by | Verified by | Date verified | Evidence / record location
EXAMPLE: CA-01 |  | Location A | Regulatory inspection | Expired license copy posted at the front counter | Renewal arrived, but no one owned replacing the posted copy | Post the current license. Add a step to the renewal SOP to replace the posted copy. | J. Rivera |  | Verified closed |  |  | M. Chen |  | EXAMPLE. Photo in the inspection folder; renewal SOP version 2
EXAMPLE: CA-02a |  | Location B | Internal walk-through | Fire exit partly blocked by a stock delivery | Immediate hazard. The cause is addressed in CA-02b. | Containment: clear the exit at once and confirm the route is open before the walk-through ends. | S. Okafor |  | Verified closed |  |  | M. Chen |  | EXAMPLE. Cleared the same day it was found. Photo of the clear exit on the walk-through sheet.
EXAMPLE: CA-02b |  | Location B | Internal walk-through | Prevent a repeat of CA-02a (blocked fire exit) | No set staging area for deliveries | Prevention: mark a delivery staging area away from exits. Add an exit check to the opening checklist. | S. Okafor |  | In progress |  |  |  |  | EXAMPLE. A separate row, owner, and date for prevention. Floor plan markup; updated opening checklist.
EXAMPLE: CA-03 |  | Location A | Audit | Two training records missing employee initials | Sign-off form has no initials field | Add an initials field. Verify the training evidence and document any late acknowledgment with its actual date. Retrain if completion cannot be established. | A. Patel |  | Done: awaiting check |  |  |  |  | EXAMPLE. Work done, but the verify-by date has passed: flagged Verification overdue.
EXAMPLE: CA-04 |  | Location B | Incident | ID scanner offline for one shift; manual checks were not logged | No written backup procedure for a scanner outage | Write an outage procedure. Train every shift lead on it. | M. Chen |  | In progress |  |  |  |  | EXAMPLE. Past due and not done: flagged Work overdue, row shows red.
EXAMPLE: CA-05 |  | Location A | Staff report | Stock room camera pointed away from the door | Camera moved during cleaning; no weekly camera check | Re-aim the camera. Add a weekly camera view check. | J. Rivera |  | In progress |  |  |  |  | EXAMPLE. Security vendor ticket; weekly check log
SPL Management · spl-management.com · Managed with Precision
General information only. Requirements vary by jurisdiction and change often; confirm current rules with your regulator or a qualified professional.
Formulas:
Overdue flag = IF([Verification overdue]="","",IF(AND(ISNUMBER([Due date]),[Due date]<TODAY(),OR([Status]="",[Status]="Open",[Status]="In progress")),"Work overdue",IF([Status]="Done: awaiting check",IF(NOT(ISNUMBER([Verify by])),"Set a verify-by date",IF([Verify by]<TODAY(),"Verification overdue","")),"")))